## gantt chart
FYP II Gantt Chart
No. | Activities | Duration (Weeks)
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
1 | Requirement Refinement & Project Planning | bar: Duration (Weeks) 1
2 | Dataset Collection and Preparation | bar: Duration (Weeks) 1 to Duration (Weeks) 2
3 | Data Preprocessing (Text Cleaning, Tokenization, TF-IDF) | bar: Duration (Weeks) 2 to Duration (Weeks) 3
4 | XGBoost Model Development and Training | bar: Duration (Weeks) 3 to Duration (Weeks) 5
5 | Model Testing and Evaluation | bar: Duration (Weeks) 5 to Duration (Weeks) 6
6 | Web System Development | bar: Duration (Weeks) 6 to Duration (Weeks) 8
7 | Claude AI Integration | bar: Duration (Weeks) 8 to Duration (Weeks) 9
8 | QA Dashboard Development | bar: Duration (Weeks) 9 to Duration (Weeks) 10
9 | System Integration and Functional Testing | bar: Duration (Weeks) 10 to Duration (Weeks) 11
10 | System Refinement and Bug Fixing | bar: Duration (Weeks) 11
11 | Final Documentation and Presentation Preparation | bar: Duration (Weeks) 11 to Duration (Weeks) 12

## roadmap
FYP II Roadmap
Phase | Title | Item | Status | Start Date | End Date | Remarks
1 | Finalise Requirements and Development Setup | 1. Finalise system requirements | TRUE | 2026-09-06 | 2026-09-06 | since fyp 1
|  | 2. Set up development environment | TRUE | 2026-09-06 | 2026-09-06 | installed python 3.13.15, git 2.55.0.5, setup all libraries, and purchase claude API (later can claim)
2 | Dataset Collection | 3. Obtain the bug report dataset | TRUE | 2026-09-07 | 2026-09-07 | use dataset eclipse_bug_records_22-07-2022.xlsx
|  | 4. Inspect the dataset | TRUE | 2026-09-07 | 2026-09-07
3 | Data Preparation | 5. Clean the dataset | TRUE | 2026-09-07 | 2026-09-07 | Data cleaning and severity mapping, done, 478,883 rows, Critical, Medium, Low mapped
|  | 6. Prepare severity labels | TRUE | 2026-09-07 | 2026-09-07
4 | NLP Pipeline | 7. Text preprocessing | TRUE | 2026-09-07 | 2026-09-07 | 478,653 rows after cleaning, 5000 TF-IDF features, both output files saved
|  | 8. Feature extraction | TRUE | 2026-09-07 | 2026-09-07
5 | XGBoost Model | 9. Split the dataset | TRUE | 2026-09-07 | 2026-09-07 | tuned model with product and component features
|  | 10. Train XGBoost | TRUE | 2026-09-07 | 2026-09-07
|  | 11. Test the model | TRUE | 2026-09-07 | 2026-09-07
|  | 12. Evaluate the model | TRUE | 2026-09-07 | 2026-09-07
|  | 13. Tune the model | TRUE | 2026-09-07 | 2026-09-07
6 | Build the Web Application | 14. Develop backend | TRUE | 2026-09-07 | 2026-09-07 | building the first phase of web application development
|  | 15. Develop bug report submission | TRUE | 2026-09-07 | 2026-09-07
7 | Integrate XGBoost Model | 16. Connect the trained model to Flask | TRUE | 2026-09-07 | 2026-09-07 | Real model connected, tested with Critical and Low examples, done. Connected trained XGBoost model to Flask
8 | Claude AI Integration | 17. Connect Claude API | TRUE | 2026-09-09 | 2026-09-09 | connected Claude API for solution recommendations
|  | 18. Display recommendation | TRUE | 2026-09-09 | 2026-09-09
9 | QA Dashboard | 19. Build the dashboard | TRUE | 2026-09-09 | 2026-09-09 | first phase, later will update and enhance
10 | Database | 20. Add MySQL | TRUE | 2026-09-09 | 2026-09-09 | auto filled right after the code is runnung
11 | System Testing | 21. Functional testing | TRUE | 2026-09-14 | 2026-10-19 | Area(Tests) Login and logout (2) Submit bug (valid flow) (1) Required-field validation (6) Bug status update (2)
|  | 22. ML testing | TRUE | 2026-09-14 | 2026-10-19
|  | 23. Integration testing | TRUE | 2026-09-14 | 2026-10-19
|  | 24. Usability testing | TRUE | 2026-09-14 | 2026-10-19
12 | Final Refinement | 25. Fix identified problems | FALSE
|  | 26. Security and reliability | FALSE
13 | Final Evaluation | 27. ML performance, AI recommendation, and system performance | FALSE
14 | Documentation and FYP II | 28. Prepare thesis | FALSE